
You are creating a customer database for the Winston Salem Warthogs minor league baseball team. Draw a project Network given the information from the book on page 193. Complete the forward and backward pass, compute the activity slack, and identify the critical path.



Critical Path: A, C, F, I, K and L activities because they cannot be stated late or the project will be finish late. Estimate finish time is 18 days, according to activity L.

Reference:

Gray, C. and Larson. (2014). Project Management, The Managerial Process, (6th). Pages 161-

177. McGaw Hill Education, ISBN 978-1-259-01070-5